## Sheet1
Risk Management Plan For Marriott International
RISK | RISK CATEGORY | PROBABILITY OF RISK 1 – 3 | IMPACT 1 – 3 | PI SCORE Prob x Impact | EXPECTED RESULT ¦ NO ACTION | RESPONSE OWNER | RESPONSE DESCRIPTION | PROBABILITY 1 – 3 KEY | IMPACT 1 – 3 KEY
External system breach | System | 2 | 3 | 6 | Shut down systems, Leading to data breaches, Service disruptions, Potential damage to the organisation's reputation | Head of IT | Shut down systems, inform employees, deny all access to systems, recovery from backups and system regeneration. | 1 | 1
Unauthorised Access | System | 2 | 3 | 6 | Data breach, Loss of customer trust, Financial and reputational damage | IT Security Team | Identify: Regularly audit user access rights. Assess: Conduct periodic reviews of access logs. Control: Implement multi-factor authentication. Monitor: Continuously monitor access logs. Report: Provide regular reports on access control status. | 2 | 2
Data Classification and Handling | Data | 2 | 2 | 4 | Unintentional exposure of sensitive information, Compromised customer data | Data Privacy Officer | Identify: Implement a data classification policy. Assess: Conduct regular audits of data handling practices. Control: Enforce encryption for sensitive data. Monitor: Monitor data access patterns. Report: Provide reports on data classification and handling compliance. | 3 | 3
Physical and Environmental Security | Hardware | 1 | 3 | 3 | Potential physical damage to data centers, Disruption of services | Facilities Management | Identify: Check CCTV footage, Assess: Identify the vulnerabilities in physical security. Control: Strengthen physical security measures. Monitor: Regularly assess environmental controls. Report: Provide reports on the status of physical and environmental security.
Inadequate Incident Response | System | 2 | 2 | 4 | Delayed detection and response to security incidents, Increased impact and scope of security breaches | Incident Response Team | Identify: Regularly update the incident response plan. Assess: Conduct drills to test the plan's effectiveness. Control: Ensure clear communication channels during incidents. Monitor: Continuously update the incident response plan. Report: Provide reports on incident response drills and improvements.
Non-compliance with Data Protection Laws | Data | 3 | 3 | 9 | Legal actions, Financial penalties and fines, and reputational damage | Legal and Compliance Team | Identify: Regularly review and update policies for compliance. Assess: Conduct regular compliance audits. Control: Implement changes to align with data protection laws. Monitor: Continuously monitor changes in data protection laws. Report: Provide reports on compliance status and actions taken.
Network Vulnerability | Network | 2 | 2 | 4 | Unauthorised access and data interception, Compromised network integrity | Network Security Team | Identify: Regularly scan and assess network vulnerabilities. Assess: Conduct penetration testing on network defenses. Control: Implement and update firewall rules and intrusion detection systems. Monitor: Continuously monitor network traffic for anomalies. Report: Provide reports on network security assessments and incidents.
Insecure Handling of Hard Documents | Hard Documents | 1 | 2 | 2 | Unauthorised access to physical documents, Loss or theft of sensitive information | Document Management Team | Identify: Implement secure storage and access controls for hard documents. Assess: Regularly audit physical document access logs. Control: Restrict physical access to document storage areas. Monitor: Periodically review access logs for unusual activity. Report: Provide reports on the security status of hard document storage.

## Risk Categories
System
Data
Hardware
Network
Hard Documents